## Worksheet
ID | Title | Case ID | Comment | Defects | Status
T139 | Verify login with valid credentials | C52 |  |  | Passed
T140 | Verify login with valid email and invalid password | C53 |  |  | Passed
T141 | Verify login with invalid email | C54 |  |  | Passed
T142 | Verify login with blank email | C55 |  |  | Passed
T143 | Verify login with blank password | C56 |  |  | Passed
T144 | Verify login with blank email and password | C57 |  |  | Passed
T145 | Verify login using email with leading spaces | C58 |  |  | Passed
T146 | Verify login using email with trailing spaces | C59 |  |  | Passed
T147 | Verify login using case variation in email | C60 |  |  | Passed
T148 | Verify logout after successful login | C61 |  |  | Passed
T149 | Verify session persistence after refresh | C62 |  |  | Passed
T150 | Verify login page accessibility from navigation | C63 |  |  | Passed
T151 | Verify forgot password link navigation | C64 |  |  | Passed
T152 | Verify account menu displayed after login | C65 |  |  | Passed
T153 | Verify password field masks entered characters | C66 |  |  | Passed
T154 | Verify Login button is clickable | C67 |  |  | Passed
T155 | Verify login using keyboard Enter key | C68 |  |  | Passed
T156 | Verify email field accepts valid email format | C69 |  |  | Passed
T157 | Verify email field validation for invalid email format | C70 |  |  | Passed
T158 | Verify copy and paste functionality in login fields | C71 |  |  | Passed
T159 | Verify user cannot access Login page after successful Signup | C72 | <p data-pasted=""true"">Expected Result:</p><p>The user should be prevented from accessing the login page and redirected appropriately.</p><p><br></p><p>Actual Result:</p><p>The user was able to access the login page after successful registration.</p><p><br></p><p>Observation:</p><p>Defect identified during execution.</p> | BUG_003 | Failed
T160 | Verify multiple clicks on Login button do not create multiple sessions | C73 |  |  | Passed
T161 | Verify user registration with valid details | C74 |  |  | Passed
T162 | Verify registration with an already registered email address | C75 |  |  | Passed
T163 | Verify registration with blank email field | C76 |  |  | Passed
T164 | Verify registration with blank password field | C77 |  |  | Passed
T165 | Verify registration with blank Repeat Password field | C78 |  |  | Passed
T166 | Verify registration when Password and Repeat Password do not match | C79 |  |  | Passed
T167 | Verify registration without selecting a security question | C80 |  |  | Passed
T168 | Verify registration without entering a security answer | C81 |  |  | Passed
T169 | Verify registration with invalid email format | C82 |  |  | Passed
T170 | Verify registration with minimum valid password requirements | C83 |  |  | Passed
T171 | Verify Register button is clickable | C84 |  |  | Passed
T172 | Verify Password field masks entered characters | C85 |  |  | Passed
T173 | Verify Repeat Password field masks entered characters | C86 |  |  | Passed
T174 | Verify registration fields accept copy and paste functionality | C87 |  |  | Passed
T175 | Verify successful navigation to Login page after registration | C88 |  |  | Passed
T176 | Verify search with an existing product name | C89 |  |  | Passed
T177 | Verify search with a partial product name | C90 |  |  | Passed
T178 | Verify search with a non-existing product name | C91 |  |  | Passed
T179 | Verify search with an empty search field | C92 |  |  | Passed
T180 | Verify search is case-insensitive | C93 |  |  | Passed
T181 | Verify search with leading and trailing spaces | C94 |  |  | Passed
T182 | Verify search with special characters | C95 | <p data-pasted=""true"">Expected Result:</p><p>The application should handle special character inputs appropriately and display relevant results or a suitable message.</p><p><br></p><p>Actual Result:</p><p>The application did not handle special character inputs as expected during search.</p><p><br></p><p>Observation:</p><p>Defect identified during execution.</p> | BUG_004 | Failed
T183 | Verify search results update dynamically | C96 |  |  | Passed
T184 | Verify clearing the search field resets the product list | C97 |  |  | Passed
T185 | Verify search field accepts copy and paste functionality | C98 |  |  | Passed
T186 | Verify logged-in user can add a product to the basket | C99 |  |  | Passed
T187 | Verify basket icon count increases after adding a product | C100 |  |  | Passed
T188 | Verify added product is displayed in the basket | C101 |  |  | Passed
T189 | Verify quantity can be increased in the basket | C102 |  |  | Passed
T190 | Verify quantity can be decreased in the basket | C103 |  |  | Passed
T191 | Verify basket total updates when quantity increases | C104 |  |  | Passed
T192 | Verify basket total updates when quantity decreases | C105 |  |  | Passed
T193 | Verify user can remove a product from the basket | C106 |  |  | Passed
T194 | Verify basket icon count decreases after removing a product | C107 |  |  | Passed
T195 | Verify empty basket message is displayed | C108 |  |  | Passed
T196 | Verify multiple products can be added to the basket | C109 |  |  | Passed
T197 | Verify the basket retains products after page refresh | C110 |  |  | Passed
T198 | Verify basket page is accessible through the basket | C111 |  |  | Passed
T199 | Verify user cannot proceed to checkout with an empty basket | C112 |  |  | Passed
T200 | Verify basket details are displayed correctly | C113 |  |  | Passed
T201 | Verify user can proceed to checkout from basket | C114 |  |  | Passed
T202 | Verify address selection page is displayed during checkout | C115 |  |  | Passed
T203 | Verify user can add a new delivery address | C116 |  |  | Passed
T204 | Verify newly added address appears in address list | C117 |  |  | Passed
T205 | Verify user can select a delivery address | C118 |  |  | Passed
T206 | Verify delivery method selection page is displayed Priority: High | C119 |  |  | Passed
T207 | Verify user can select a delivery method | C120 |  |  | Passed
T208 | Verify payment page is displayed | C121 |  |  | Passed
T209 | Verify user can add a new payment method | C122 |  |  | Passed
T210 | Verify added payment method appears in payment list | C123 |  |  | Passed
T211 | Verify user can select a payment method | C124 |  |  | Passed
T212 | Verify order summary page displays correct information | C125 |  |  | Passed
T213 | Verify user can place an order successfully | C126 |  |  | Passed
T214 | Verify order confirmation displays order details | C127 |  |  | Passed
T215 | Verify basket is emptied after successful order | C128 |  |  | Passed
T216 | Verify Forgot Password page is accessible from Login page | C129 |  |  | Passed
T217 | Verify security question is displayed for a registered email address | C130 |  |  | Passed
T218 | Verify password reset with valid details | C131 |  |  | Passed
T219 | Verify password reset with incorrect security answer | C132 |  |  | Passed
T220 | Verify password reset with blank email field | C133 |  |  | Passed
T221 | Verify password reset with blank security answer | C134 |  |  | Passed
T222 | Verify password reset when New Password and Repeat Password do not match | C135 |  |  | Passed
T223 | Verify user can login using the newly reset password | C136 |  |  | Passed
T224 | Verify user can logout successfully | C137 |  |  | Passed
T225 | Verify authenticated pages are inaccessible after logout | C138 | <p data-pasted=""true"">Expected Result:</p><p>Authenticated pages should not be accessible after logout.</p><p><br></p><p>Actual Result:</p><p>Authenticated pages remained accessible after the user logged out.</p><p><br></p><p>Observation:</p><p>Defect identified during execution.</p> | BUG_005 | Failed
T226 | Verify user session is terminated after logout | C139 |  |  | Passed
T227 | Verify account-related options are hidden after logout | C140 |  |  | Passed
T228 | Verify user can login again after logging out | C141 |  |  | Passed
T229 | Verify User Profile page is accessible | C142 |  |  | Passed
T230 | Verify registered email address is displayed on the Profile page | C143 |  |  | Passed
T231 | Verify user can update the username | C144 |  |  | Passed
T232 | Verify profile changes persist after page refresh | C145 |  |  | Passed
T233 | Verify profile picture upload option is available | C146 |  |  | Passed
T234 | Verify user-specific information is not visible after logout | C147 |  |  | Passed
T235 | Verify Order History page is accessible | C148 |  |  | Passed
T236 | Verify previously placed orders are displayed | C149 |  |  | Passed
T237 | Verify order details are displayed correctly | C150 |  |  | Passed
T238 | Verify latest order appears in Order History after checkout | C151 |  |  | Passed
T239 | Verify Order History page behavior when no orders exist | C152 |  |  | Passed
T240 | Verify Order History is inaccessible after logout | C153 | <p data-pasted=""true"">Expected Result:</p><p>Order History should not be accessible after logout.</p><p><br></p><p>Actual Result:</p><p>The Order History page remained accessible after the user logged out.</p><p><br></p><p>Observation:</p><p>Defect identified during execution.</p> | BUG_006 | Failed
T241 | Verify side navigation menu opens successfully | C154 |  |  | Passed
T242 | Verify ""All Products"" menu option redirects to Home page | C155 |  |  | Passed
T243 | Verify ""Photo Wall"" menu option navigation | C156 |  |  | Passed
T244 | Verify ""About Us"" menu option navigation | C157 |  |  | Passed
T245 | Verify side navigation menu closes successfully | C158 |  |  | Passed
T246 | Verify Customer Feedback page is accessible | C159 |  |  | Passed
T247 | Verify logged-in user's email is auto-populated in the Author field | C160 |  |  | Passed
T248 | Verify feedback can be submitted with valid details | C161 |  |  | Passed
T249 | Verify feedback cannot be submitted without mandatory details | C162 |  |  | Passed
T250 | Verify Submit button functionality on the Customer Feedback form | C163 |  |  | Passed
T251 | Verify About Us page is accessible | C164 |  |  | Passed
T252 | Verify About Us page displays company information correctly | C165 |  |  | Passed
T253 | Verify links available on the About Us page are functional | C166 | <p data-pasted=""true"">Expected Result:</p><p>All links available on the About Us page should function correctly.</p><p><br></p><p>Actual Result:</p><p>One or more links on the About Us page were not functioning as expected.</p><p><br></p><p>Observation:</p><p>Defect identified during execution.</p> | BUG_007 | Failed